## Schedule
Schedule
Overview |  |  | Week 6 | Week 7 | Week 8
Liv | Homepage | - navigation tabs | 17-23 March | 24-30 March | 31 March - 6 April
|  | - Leaf it out logo |  |  | Competition date - 4th April
|  | - intro - 2 sentences. Slogan and mission | 1. Have text for each webpage ready. | 1. Complete HTML. | 1. Complete CSS.
|  | - heading photo - maybe a slideshow? | 2. Have the layout for each webpage ready. | 2. Start on CSS. | 2. Complete interactive bits with JavaScript.
|  | - social media and contact | 3. Upload pictures of layout on Github. | 3. Think about which bits will be interactive. | 3. Have the full website ready by Wednesday.
Steph | Food | - list of ingredient |  | 4. Think about questions we may need to ask. | 4. Think about how we will present.
|  | - 3 recipes |  | 5. Make a checklist of things we must have/use in the website. | 5. Maybe meet at 6:15pm on Thursday to go over everything??
|  | - put them in columns or also in a slideshow? |  | 6. Make sure we do all things on the list. | 6. Go over the checklist one last time.
Rosie | Government | - mission statement |  | 8. Set-up the GitHub and work there.
- quiz
- SDGs
- sustainability checklist
- organisations
Anca | Sustainable living | - external links to products
- everyday products and their sustainable alternatives
- explain each of them